## Backlog Mock
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Initial web UI scaffold | High | Ved-Joshi | Done | 2026-03-03 | 2026-03-03 | M1 Foundation | React web shell + base pages | First frontend baseline commit
Backend service bootstrap | High | Hazelette | Done | 2026-03-04 | 2026-03-06 | M1 Foundation | FastAPI backend skeleton + config + auth security modules | Includes JWT/password hashing foundations
Supabase integration for auth and accounts | High | Anishka Chauhan | Done | 2026-03-10 | 2026-03-10 | M1 Foundation | Supabase connection + account creation/login wiring | Multiple same-day setup commits
Database migrations and RLS hardening | High | Hazelette | Done | 2026-03-16 | 2026-03-16 | M2 Platform Hardening | Migrations + schema constraints + RLS policy patches | SQLite removed and Supabase-first architecture finalized
Complete registration edge function | High | Hazelette | Done | 2026-03-21 | 2026-03-23 | M2 Platform Hardening | Registration edge function with profile provisioning | Later hardened payload validation and CORS support
MFA flow integration and gating | Medium | Hazelette | Done | 2026-03-23 | 2026-03-23 | M2 Platform Hardening | MFA enroll/challenge + login gating and redirects | Subsequently relaxed/disabled for product flow changes
Backend banking read APIs | High | Ved-Joshi | Done | 2026-03-23 | 2026-03-23 | M3 Core Banking APIs | Accounts/transactions/payments/deposits/notifications read endpoints | Enabled frontend migration off mocks
Frontend migration to backend APIs | High | Ved-Joshi | Done | 2026-03-23 | 2026-03-23 | M3 Core Banking APIs | Dashboard + transactions + accounts integrated with live backend | Included empty-state handling
Account creation/open-close workflows | High | Ved-Joshi | Done | 2026-03-23 | 2026-04-08 | M3 Core Banking APIs | Account open/close UX + backend validations | Refined via follow-up UX and bugfix commits
Internal transfer engine with scheduling | High | Ved-Joshi | Done | 2026-03-23 | 2026-04-17 | M4 Money Movement | Immediate + scheduled + recurring internal transfers | Runner hardening and stale transfer recovery added
ATM locator with Google Maps integration | Medium | Ved-Joshi | Done | 2026-03-25 | 2026-03-25 | M5 Customer Experience | Live ATM search + hours + caching + UI refinements | Series of focused UX improvements
Dockerization + compose runtime | High | Anishka Chauhan | Done | 2026-04-08 | 2026-04-24 | M6 DevOps | Containerized frontend/backend + docker compose setup | Later fixes to compose/runtime behavior
Admin panel implementation | Medium | Anishka Chauhan | Done | 2026-04-08 | 2026-04-27 | M7 Operations | Admin UI and account reporting screens | Delivered across multiple incremental commits
Account/transfer module backend refactor | High | Hazelette | Done | 2026-04-11 | 2026-04-22 | M4 Money Movement | Service and router decomposition for accounts/transfers/transactions | Marked some legacy files for later cleanup
Bill pay lifecycle and cadence support | High | Ved-Joshi | Done | 2026-04-20 | 2026-04-23 | M4 Money Movement | Bill pay create/retry/cancel + daily/weekly/monthly cadence support | Includes schedule-date alignment and retry-state fixes
Member + external transfer flows | High | Ved-Joshi | Done | 2026-04-22 | 2026-04-23 | M4 Money Movement | Recipient resolution + external accounts + scheduled edit/retry | Validation hardening and timeline UX refinements included
Ledger postings for bill pay/deposit/withdrawal | High | Hazelette | Done | 2026-04-25 | 2026-04-27 | M8 Ledger Integrity | Double-entry ledger integration for money-in/out and bill pay disbursement | Includes omitted notification/disbursement fixes
Deposit upload hardening and withdrawal support | High | Ved-Joshi | Done | 2026-04-26 | 2026-04-26 | M4 Money Movement | Check upload session hardening + ATM deposit/withdrawal UX/API fixes | Addressed race/expiry and copy-text bugs
Mobile parity: Initial web UI scaffold | High | Joshua | Done | 2026-03-03 | 2026-03-03 | M1 Foundation | Mobile implementation parity for React web shell + base pages | Mobile app implemented the same feature flow in tandem with web delivery.
Mobile parity: Frontend migration to backend APIs | High | Joshua | Done | 2026-03-23 | 2026-03-23 | M3 Core Banking APIs | Mobile implementation parity for Dashboard + transactions + accounts integrated with live backend | Mobile app implemented the same feature flow in tandem with web delivery.
Mobile parity: ATM locator with Google Maps integration | Medium | Joshua | Done | 2026-03-25 | 2026-03-25 | M5 Customer Experience | Mobile implementation parity for Live ATM search + hours + caching + UI refinements | Mobile app implemented the same feature flow in tandem with web delivery.
Mobile parity: Admin panel implementation | Medium | Joshua | Done | 2026-04-08 | 2026-04-08 | M7 Operations | Mobile implementation parity for Admin UI and account reporting screens | Mobile app implemented the same feature flow in tandem with web delivery.
Admin dashboard KPI cards and account-monitoring widgets | High | Anishka Chauhan | Done | 2026-04-09 | 2026-04-09 | M7 Operations | Admin dashboard summary cards with account health visibility | Changed: Admin dashboard KPI and monitoring widgets. Scope: Implement admin overview cards and account health indicators.